**Food Africa – *Empowering Youth and Promoting Innovative PPPs through More Efficient Agro-Food Value Chains in Nigeria and Beyond***

**Integrated Monitoring Evaluation and Research Framework:**

|  |  |  |  |
| --- | --- | --- | --- |
| **Activity types** | **Year I** | **Year II** | **Year III** |
| **Studies and surveys** | **Baseline study:** will allow for profiling of beneficiaries during the project inception phase. All data will be sex disaggregated to allow for a gender responsive monitoring framework. | **Feasibility study** will be conducted **to establish food processing facilities**  **Value chain studies** targeting 3-4vegetables  **Gender study** focusing on women beneficiaries to further information project interventions  **Study on international market opportunities for specialized horticultural products from Northern Nigeria** | **Case studies** documentingexperiences of targeted beneficiariesidentified in year I baseline study/profiling exercise |
| **Evaluations** |  | **Mid-term review** will beconducted internally in the mid to latter part of year II by project partners to take stock and identify good practices which will be scaled up in year III | **Final evaluation and end line study** will be conducted in accordance with international norms and best practice and will include a dissemination plan for the evaluation findings |
| **M&E systems** | Monitoring reports submitted on six monthly basis | Monitoring reports submitted on six monthly basis | Monitoring reports submitted on six monthly basis |
| **M&E capacity building** | **M&E strategy** will be developed by Project Management Unit | On-going guidance and support on M&E provided by SDG Fund Secretariat | On-going guidance and support on M&E provided by SDG Fund Secretariat |
| **Landmark events** | Project Kick Off | **Policy and inter-sectorial coordination consultations** and **final workshop** targeting policymakers  **Official inauguration** of food processing facilities | Ceremony for grant awardees  **Project closing ceremony**: High profile event organized by partners for accountability. |
| **M&E activities of partners** | Planning workshop: technical meeting with project implementing partners to review and adjust AWP and Performance Framework based on actual starting date. Detailed division of M&E roles and responsibilities. | Ongoing data collection according to division of roles and responsibilities in line with M&E Framework.  Monitoring missions conducted to identify bottlenecks and corrective actions. | Ongoing data collection, review and analysis according to division of roles and responsibilities in line with M&E Framework. |
| **Publications** |  | **Feasibility studies**  **Value chain studies** targeting 3-4 vegetables  **Gender study** focusing on women in KadunaState and neighbouring regions  **Study on specialized horticultural products from Northern Nigeria**  **Study on**  **policy and inter-sectorial coordination** | **Case studies** documenting human stories and results  Digital versions of final evaluation and end line study will be disseminated online on SDG Fund website |