**Food Africa – *Empowering Youth and Promoting Innovative PPPs through More Efficient Agro-Food Value Chains in Nigeria and Beyond***

**Performance Monitoring Framework / SDG-F Project Promoting Innovative PPPs**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **1. Results** | **2. Performance indicators** | **3. Data sources** | **4. Collection methods** | **5. Frequency** | **6. Responsible** | **7. Baseline** | **8. Budget** |
| 1.1 Improved food security and nutrition and poverty alleviation through strengthening of the agro-food value chains, improving agricultural productivity and yields, creation of food processing facilities and promotion of access to markets in Kaduna, Nigeria. | Food processing facilities built and operational | Project/ official records from processing facility On-site visits Photographic evidence | Project/ official records cross-referenced with processing facility records and visual materials. | Quarterly  | Project Management Unit | No processing facility in Jere area  | Total budget for all M&E – USD 95,000 approx.(3.6% of total costs) |
| Successful transition of facilities to public-private ownership by project closure | Project/ official records  | Project/ official records | Quarterly  | Project Management UnitFacility Manager  | No processing facility in Jere area  |
| Buyers found by end of the project to ensure equitable sale of and increased volume of market compliant produce | Facilities’ records, contracts signed with buyers  | Project/ official records | Quarterly  | Project Management UnitFacility Manager  | None  |
| 1,500 farmers selling produce to food processing facility | Facilities’ records, contracts signed with cooperatives/ farmer based organizations  | Project/ official records | Quarterly  | Project Management UnitFacility Manager  | None  |
| 25 farmers/ farmer based organizations registered in database (10-15 farmers each)year I; 50 by year II | Facilities’ records, project routine reporting  | Project/ official records | Quarterly  | Facility Manager Project Management Unit | None  |
| Increase of XX registered cooperatives, 25% led by women in outgrowers’ scheme | Project, government records | Project, government records | Quarterly  | Project Management Unit | **TBC**13 in immediate project area  |
| 1.2 Improved local institutional capacities for vocational training in agriculture and agro-processing | 20 Trainers/ Community Facilitators, including 7 women trained through ToT programme | Contracts signed with Trainers End of traineeship feedback questionnaire  | Contracts signed with Trainers End of traineeship feedback questionnaire  | Inception period End of traineeship | Facility Manager Project Management Unit | None |
| 25 farmer based organizations using facility trained  | Baseline reportEnd line study  | Baseline reportEnd line study  | Inception period Project closure  | Project Management Unit | No such traineeship opportunity in the area  |
| 40% increase in yields20% increase in revenues  | Baseline reportEnd line study  | Baseline reportEnd line study  | Inception period Project closure  | Project Management Unit | No data available  |
| Vocational/business skills training programme  | Training records verified by survey data from youth interview | Project administrative records and training completion questionnaires. | Quarterly  | Project Management Unit | No data available |
| 1.3 Improved policy and inter-sectorial coordination  | Policy gap study completed  | Policy gap study | Policy gap study report  | End of year II | Project Management Unit | No inter-sectoral study – TBC |
| Results and recommendations disseminated  | Study and consultations on recommendations for inter-sectoral coordination completed | Study and consultations on recommendations for inter-sectoral coordination completed | End of year III | Project Management Unit | No inter-sectoral study – TBC |
| 2.1 Local economic development, outreach and networks and sources of new livelihoods created in Kaduna through a hub promoting trade in agro-produce and other local goods and services | 500 young people of which 250 women assisted to starting income generating activities or strengthening their existing small businesses | Project records/ training records and follow-up questionnaires, mid-term review  | Project records/ training records and follow-up questionnaires, report from mid-term review  | Quarterly  | Project Management Unit | XX trained under FAO project targeting youth in agriculture in Kaduna, TBC |
| 100 small grants competitively allocated  | Grant letters and contracts | Grant letters and contracts | Quarterly | Project Management Unit | None  |
| 300 farmers using app | Project records  | Project records | Quarterly | Project Management Unit | 300 farmers under FAO’s ongoing AMIS project  |
| 3.1 Scaling Up and Replication of project results in consultation with all project partners | Identification of XX good practices for scaling up in year III | Mid-term review  | Report from mid-term review | Q3 of year II | Project Management Unit/ Board of Trustees  |  |
| Target 3.1b. XX finance and partners scoped and identified for scaling up in year III | Mid-term review  | Report from mid-term review | Q3 of year II | Project Management Unit/ Board of Trustees  |  |